## Project Scope & Schedule
PROJECT SCOPE & PAYMENT SCHEDULE |  |  |  | CABRERA CONSTRUCTION
Project Scope: |  |  | Contract Date: |  | Contract Type: | Fixed-Price Agreement
Job Site Location: |  |  | Payment Terms: |  | Total Price:
PROJECT PARTIES, SITE DETAILS & SCHEDULE
CLIENT (PROPERTY OWNER) |  | LICENSED GENERAL CONTRACTOR |  | PROJECT TIMELINE & SITE
Client Name: | Owner | Cabrera Construction (Lic. #1135927) • +1 (415) 359-5394 |  | Timeline:
Client Email: | Owner email | admin@cabrera.construction • 2752 Capistrano St, Antioch, CA |  | Job Site Location:
TOTAL CONTRACT PRICE | INITIAL DEPOSIT | PROJECT SCOPE | PROJECT DURATION |  | MILESTONES
Fixed-Price Agreement | Due Upon Signing | Full Enclosure & Tile Renovation | Sept 24 – Oct 16, 2026 |  | Milestones 0 through 3
* Municipal Permit Contingency Note: If municipal building permits and city inspections are mandated, the estimated total contract price increases to $21,200.00.
Milestone # | Milestone Title & Deliverable | Detailed Scope of Work & Verification Criteria | Target Due Date | Amount ($) | % of Total | Payment Status
TOTAL CONTRACT | Total Fixed Contract Value |  |  | 0 | 0% | Balanced (100%)
MATERIAL SUPPLY & RESPONSIBILITY MATRIX
Item Category | Material Description | Quantity / Coverage Area | Supplied By | Installed / Hauled By | Approval & Operational Notes
WORKMANSHIP WARRANTY & QUALITY ASSURANCE
Warranty Policy & Term | 1 Year Workmanship Guarantee (CSLB Compliant): Cabrera Construction warrants all workmanship for one full year from the date of final completion (October 16, 2026).
Standard Exclusions | Excludes normal wear and tear, direct flooding or water damage unrelated to installation, subfloor/wall structural settling, ambient humidity extremes, or manufacturing flaws and material defects in owner-supplied fixtures or tile.
Service Procedure | Submit written notification to admin@cabrera.construction or call +1 (415) 359-5394. Cabrera Construction will schedule an on-site inspection and initiate corrective warranty repair within 5 business days.
CONTRACT ACCEPTANCE & SIGNATURE ACKNOWLEDGMENT
By signing below, both parties acknowledge and agree to the specifications, milestone payment schedule, material responsibilities, and 1-year workmanship warranty set forth in this Agreement.
CLIENT / PROPERTY OWNER ACCEPTANCE |  |  | LICENSED CONTRACTOR ACCEPTANCE
Authorized Signature: | X __________________________________________ |  | Authorized Signature: | X __________________________________________
Printed Name: |  |  | Printed Name: | Sam Cabrera (Lic. #1135927)
Date Signed: |  |  | Date Signed: